## Executive Summary
A64 Core Platform - Vendor Security Compliance Assessment
Assessment Date: 2026-02-04 ¦ Platform Version: v1.10.0 ¦ Classification: CONFIDENTIAL
Metric | Value
Total Controls Assessed | 25
Fully Compliant | 5
Partially Compliant | 16
Non-Compliant | 4
Overall Score (Full) | 20%
Overall Score (Partial+Full) | 84%
# | Control Area | Status | Priority | Phase
1 | Cryptography (Encryption, Decryption) | PARTIAL | HIGH | Phase 3
2 | Certificate Management (SSL, TLS) | PARTIAL | MEDIUM | Phase 3
3 | Software Development Lifecycle | PARTIAL | HIGH | Phase 2
4 | Integration Requirements | PARTIAL | MEDIUM | Phase 2
5 | Hosting and Publishing | PARTIAL | MEDIUM | Phase 2
6 | Data Protection (Backup/Storage/Restore) | PARTIAL | CRITICAL | Phase 1
7 | Log Monitoring and Traceability | PARTIAL | HIGH | Phase 2
8 | Security Configurations & Hardening | PARTIAL | HIGH | Phase 1
9 | Database Security | PARTIAL | HIGH | Phase 1
10 | Authentication & Authorization | PARTIAL | CRITICAL | Phase 1
11 | Business Continuity & DR | PARTIAL | CRITICAL | Phase 1
12 | Secure Remote Access | PARTIAL | MEDIUM | Phase 2
13 | Privilege Identity & Access Mgmt | PARTIAL | HIGH | Phase 2
14 | Security Assessment (VA/PT) | PARTIAL | CRITICAL | Phase 1
15 | Application Protection (WAF) | NON-COMPLIANT | HIGH | Phase 2
16 | DDoS Protection (IDS/IPS) | NON-COMPLIANT | HIGH | Phase 2
17 | Capacity Management & Planning | PARTIAL | MEDIUM | Phase 3
18 | Communication & Collaboration | PARTIAL | MEDIUM | Phase 3
19 | Supplier Relationship | NON-COMPLIANT | HIGH | Phase 2
20 | Availability Management | NON-COMPLIANT | HIGH | Phase 2
21 | Segregated Environments | PARTIAL | HIGH | Phase 2
22 | Policy Compliance | PARTIAL | HIGH | Phase 3
23 | RBAC & Segregation of Duties | PARTIAL | MEDIUM | Phase 2
24 | Data Security (Flow/Classification) | NON-COMPLIANT | HIGH | Phase 2
25 | Security Architecture | PARTIAL | MEDIUM | Phase 3

## Detailed Controls
# | Control Area | Sub-Control | Status | Evidence / Current State | Gap / Finding | Remediation Action | Priority | Phase | Owner | Target Date | Completion Date | % Done | Notes
1 | Cryptography | Password hashing | COMPLIANT | bcrypt cost factor 12 (src/utils/security.py:17-52) |  |  | N/A | Done |  |  |  | 100%
1 | Cryptography | License key encryption | COMPLIANT | Fernet AES-128-CBC + HMAC, PBKDF2-SHA256 100k iter (src/utils/encryption.py) |  |  | N/A | Done |  |  |  | 100%
1 | Cryptography | JWT signing | COMPLIANT | HS256 HMAC-SHA256 (src/utils/security.py:55-99) |  |  | N/A | Done |  |  |  | 100%
1 | Cryptography | Data-at-rest encryption | NON-COMPLIANT | MongoDB and MySQL not encrypted at rest | No encryption at rest configured | Enable MongoDB WiredTiger encryption; Enable MySQL TDE | HIGH | Phase 3 |  |  |  | 0%
1 | Cryptography | Data-in-transit encryption | PARTIAL | TLS on Nginx prod; internal HTTP between containers | Internal service communication unencrypted | Implement mTLS between containers | MEDIUM | Phase 3 |  |  |  | 50%
1 | Cryptography | Key management | NON-COMPLIANT | SECRET_KEY in env var, no rotation | No HSM, no key rotation policy | Implement AWS KMS or HashiCorp Vault; define key rotation policy | HIGH | Phase 3 |  |  |  | 0%
1 | Cryptography | Crypto algorithm governance | NON-COMPLIANT | No documented policy | No approved algorithm list | Create cryptographic standards policy document | MEDIUM | Phase 3 |  |  |  | 0%
2 | Certificate Management | SSL/TLS certificates | COMPLIANT | Let's Encrypt for a64core.com (nginx/nginx.prod.conf) |  |  | N/A | Done |  |  |  | 100%
2 | Certificate Management | TLS version control | COMPLIANT | TLSv1.2 and TLSv1.3 only |  |  | N/A | Done |  |  |  | 100%
2 | Certificate Management | Cipher suite hardening | COMPLIANT | ECDHE-ECDSA/RSA with AES-GCM |  |  | N/A | Done |  |  |  | 100%
2 | Certificate Management | Certificate renewal automation | NON-COMPLIANT | No certbot auto-renewal cron | Certificates may expire without warning | Set up certbot auto-renewal cron job with pre/post hooks | MEDIUM | Phase 3 |  |  |  | 0%
2 | Certificate Management | Certificate monitoring | NON-COMPLIANT | No expiry alerting | No alerts before certificate expiry | Implement cert expiry monitoring (30/14/7 day warnings) | MEDIUM | Phase 3 |  |  |  | 0%
2 | Certificate Management | Internal certificates | NON-COMPLIANT | No internal CA | No service-to-service TLS | Implement internal CA for container mTLS | LOW | Phase 3 |  |  |  | 0%
3 | SDLC | Source code management | COMPLIANT | Git repository with proper .gitignore |  |  | N/A | Done |  |  |  | 100%
3 | SDLC | Environment separation | PARTIAL | Dev + Prod Docker Compose | No staging environment | Create docker-compose.staging.yml; separate infrastructure | HIGH | Phase 2 |  |  |  | 50%
3 | SDLC | CI/CD pipeline | PARTIAL | GitHub Actions: security-scan.yml (black, flake8, pip-audit, npm audit, Trivy), build.yml (API tests, frontend build, compose validation) | Pipelines created; deploy stage not yet implemented | Implement GitHub Actions with lint, test, scan, deploy stages | HIGH | Phase 2 |  |  |  | 70% | CI pipelines created and first scans run 2026-02-04
3 | SDLC | Code review process | NON-COMPLIANT | No PR requirements | No branch protection or review policies | Enable branch protection on main; require PR reviews | HIGH | Phase 2 |  |  |  | 0%
3 | SDLC | Secure coding standards | PARTIAL | CLAUDE.md guidelines; black/flake8/mypy available | Not enforced in CI | Add linting enforcement to CI pipeline | MEDIUM | Phase 2 |  |  |  | 30%
4 | Integration Requirements | API documentation | COMPLIANT | FastAPI auto-generated Swagger + API-Structure.md (112KB) |  |  | N/A | Done |  |  |  | 100%
4 | Integration Requirements | Service catalogue | PARTIAL | Docker Compose defines services | No formal service catalogue with SLAs | Create formal service catalogue with SLA definitions | MEDIUM | Phase 2 |  |  |  | 40%
4 | Integration Requirements | API gateway | NON-COMPLIANT | Nginx as reverse proxy only | No dedicated API gateway | Consider Kong or AWS API Gateway | MEDIUM | Phase 2 |  |  |  | 0%
5 | Hosting & Publishing | Cloud hosting | COMPLIANT | AWS me-central-1 (UAE region) |  |  | N/A | Done |  |  |  | 100%
5 | Hosting & Publishing | Internet exposure | PARTIAL | Nginx reverse proxy; Adminer exposed in dev | Adminer in production risk | Remove Adminer from production; restrict database ports | HIGH | Phase 2 |  |  |  | 50%
5 | Hosting & Publishing | Data residency | PARTIAL | Data in UAE region | No data residency policy documented | Document data residency policy | MEDIUM | Phase 3 |  |  |  | 50%
6 | Data Protection | Backup procedures | PARTIAL | scripts/backup/mongodb_backup.sh, docker/backup/Dockerfile, docker-compose backup service | Local backups only; no S3/off-site upload yet | Add S3 upload and backup encryption | CRITICAL | Phase 1 |  |  |  | 70% | Backup infra implemented 2026-02-04; daily 2AM UTC cron, 7/4/3 retention
6 | Data Protection | Backup encryption | NON-COMPLIANT | No encrypted backups | Backups unprotected | Encrypt backups with GPG/KMS before S3 upload | CRITICAL | Phase 1 |  |  |  | 0% | Backup scripts ready; encryption layer TODO
6 | Data Protection | Restore testing | PARTIAL | scripts/backup/mongodb_restore.sh with validation and confirmation | Restore script exists; quarterly test schedule not yet executed | Document and test restore procedures quarterly | CRITICAL | Phase 1 |  |  |  | 50% | Restore script created 2026-02-04; first test pending
6 | Data Protection | Data retention policy | PARTIAL | Backup retention: 7 daily, 4 weekly, 3 monthly (scripts/backup/README.md) | Backup retention defined; data lifecycle retention policy still needed | Define data retention policy per data type | HIGH | Phase 1 |  |  |  | 30% | Backup retention policy defined 2026-02-04
6 | Data Protection | Data classification | NON-COMPLIANT | No classification scheme | Cannot apply controls by sensitivity | Create Public/Internal/Confidential/Restricted classification | HIGH | Phase 1 |  |  |  | 0%
7 | Log Monitoring | Application logging | PARTIAL | Python logging with basic format | Not structured JSON, no correlation IDs | Implement structured JSON logging with request correlation IDs | HIGH | Phase 2 |  |  |  | 30%
7 | Log Monitoring | Docker container logging | COMPLIANT | JSON-file driver, 10MB rotation, 3 files per service |  |  | N/A | Done |  |  |  | 100%
7 | Log Monitoring | Audit logging | PARTIAL | Module audit log collection exists | No comprehensive security event audit trail | Create audit logging for login, permission changes, data access, admin actions | HIGH | Phase 2 |  |  |  | 20%
7 | Log Monitoring | SIEM integration | NON-COMPLIANT | No SIEM configured | No security event correlation | Integrate with SIEM (Splunk/QRadar/AWS SecurityHub) | HIGH | Phase 2 |  |  |  | 0%
7 | Log Monitoring | Log aggregation | NON-COMPLIANT | Logs only in containers | No centralized logging | Set up ELK Stack, Loki, or CloudWatch Logs | HIGH | Phase 2 |  |  |  | 0%
8 | Security Hardening | Input validation | COMPLIANT | Pydantic models on all 43+ endpoints |  |  | N/A | Done |  |  |  | 100%
8 | Security Hardening | Security headers (existing) | COMPLIANT | HSTS, CSP, Permissions-Policy, X-Permitted-Cross-Domain-Policies added to nginx.prod.conf and nginx.dev.conf |  |  | N/A | Done |  |  | 2026-02-04 | 100% | All security headers implemented 2026-02-04
8 | Security Hardening | Container hardening | PARTIAL | Non-root user in Dockerfile | Docker socket mounted, API runs as root in dev | Use Docker socket proxy; run as non-root in prod | HIGH | Phase 1 |  |  |  | 50%
8 | Security Hardening | Database hardening | PARTIAL | MongoDB auth enabled (mongo-init/init-user.js), ports closed in prod (docker-compose.prod.yml), Adminer disabled | CIS Docker benchmarks not yet run | Run CIS Docker Benchmark; implement additional OS-level hardening | CRITICAL | Phase 1 |  |  |  | 70% | MongoDB auth + port closure implemented 2026-02-04
8 | Security Hardening | CIS/NIST benchmarks | NON-COMPLIANT | No benchmark compliance verification | No CIS Docker or NIST mapping | Run CIS Docker Benchmark; map controls to NIST CSF | MEDIUM | Phase 3 |  |  |  | 0%
9 | Database Security | Database authentication | COMPLIANT | MongoDB auth with dedicated a64core_app user (readWrite only); root user separate; prod enforced via --auth flag |  |  | N/A | Done |  |  | 2026-02-04 | 100% | MongoDB auth implemented 2026-02-04; least-privilege app user
9 | Database Security | Data masking | PARTIAL | Passwords excluded from API responses | No field-level masking | Implement data masking for PII fields | MEDIUM | Phase 2 |  |  |  | 40%
9 | Database Security | Data anonymization | NON-COMPLIANT | No anonymization for non-prod | Production data risk in dev/staging | Create data anonymization scripts for non-production environments | MEDIUM | Phase 2 |  |  |  | 0%
9 | Database Security | Encryption at rest | NON-COMPLIANT | Neither DB encrypted at rest | Data exposed if disk compromised | Enable MongoDB WiredTiger encryption; MySQL TDE | HIGH | Phase 2 |  |  |  | 0%
9 | Database Security | Query parameterization | COMPLIANT | MongoDB Motor/PyMongo driver; Pydantic validation |  |  | N/A | Done |  |  |  | 100%
10 | Auth & AuthZ | Authentication mechanism | COMPLIANT | JWT-based with bcrypt passwords (src/utils/security.py) |  |  | N/A | Done |  |  |  | 100%
10 | Auth & AuthZ | Password policy | COMPLIANT | 8+ chars, upper/lower/number/special required |  |  | N/A | Done |  |  |  | 100%
10 | Auth & AuthZ | Account lockout | COMPLIANT | Redis-backed: 5 failed attempts, 15-min lockout (src/middleware/rate_limit.py); distributed across instances |  |  | N/A | Done |  |  |  | 100% | Migrated to Redis-backed rate limiting 2026-02-04
10 | Auth & AuthZ | Token management | COMPLIANT | Rotating refresh tokens, 1h access, 7d refresh |  |  | N/A | Done |  |  |  | 100%
10 | Auth & AuthZ | RBAC | COMPLIANT | 5-level hierarchy: SuperAdmin>Admin>Mod>User>Guest |  |  | N/A | Done |  |  |  | 100%
10 | Auth & AuthZ | MFA / 2FA | NON-COMPLIANT | Not implemented | Single-factor authentication only | Implement TOTP-based MFA (Google Authenticator/Authy) | CRITICAL | Phase 1 |  |  |  | 0%
10 | Auth & AuthZ | SSO | NON-COMPLIANT | Not implemented | No enterprise SSO | Implement SAML 2.0 or OpenID Connect | HIGH | Phase 2 |  |  |  | 0%
10 | Auth & AuthZ | Session management | COMPLIANT | DB-backed sessions with revocation (auth_service.py) |  |  | N/A | Done |  |  |  | 100%
11 | BC & DR | Business Impact Analysis | PARTIAL | Docs/2-Working-Progress/Business-Impact-Analysis.md - template with process mapping and priorities | Template created; requires organizational review and approval | Create BIA document identifying critical business processes | CRITICAL | Phase 1 |  |  |  | 60% | BIA template created 2026-02-04; pending stakeholder review
11 | BC & DR | DR Plan | PARTIAL | Docs/2-Working-Progress/Disaster-Recovery-Plan.md - comprehensive plan with 4 runbooks | Plan created; requires testing and organizational approval | Create comprehensive DR plan with runbooks | CRITICAL | Phase 1 |  |  |  | 60% | DR plan with runbooks created 2026-02-04; pending DR test
11 | BC & DR | RTO/RPO definition | PARTIAL | RTO: 4h, RPO: 1h defined in Disaster-Recovery-Plan.md | Targets defined; not yet validated through DR testing | Define RTO (suggest 4h) and RPO (suggest 1h) | CRITICAL | Phase 1 |  |  |  | 60% | RTO/RPO defined 2026-02-04; validation pending
11 | BC & DR | DR testing | PARTIAL | Quarterly DR test schedule defined in Disaster-Recovery-Plan.md | Schedule defined; first test not yet conducted | Schedule quarterly DR tests; document results | HIGH | Phase 1 |  |  |  | 30% | DR test schedule created 2026-02-04; first test to be scheduled
11 | BC & DR | Failover procedures | NON-COMPLIANT | Single instance, no failover | Single point of failure | Implement MongoDB replica set; multi-AZ deployment | HIGH | Phase 2 |  |  |  | 0%
12 | Secure Remote Access | SSH access | COMPLIANT | Key-based SSH with PEM file |  |  | N/A | Done |  |  |  | 100%
12 | Secure Remote Access | SSH access control | COMPLIANT | AWS Security Group IP restriction + update script |  |  | N/A | Done |  |  |  | 100%
12 | Secure Remote Access | VPN | NON-COMPLIANT | No VPN configured | Direct SSH to production | Implement AWS Client VPN or WireGuard | MEDIUM | Phase 2 |  |  |  | 0%
12 | Secure Remote Access | Bastion host | NON-COMPLIANT | Direct SSH to production server | No jump box | Set up bastion host; consider AWS SSM Session Manager | MEDIUM | Phase 2 |  |  |  | 0%
13 | Privilege IAM | RBAC implementation | COMPLIANT | 5-level role hierarchy with middleware (permissions.py) |  |  | N/A | Done |  |  |  | 100%
13 | Privilege IAM | Password vault | NON-COMPLIANT | No vault configured | Secrets in environment variables | Implement AWS Secrets Manager or HashiCorp Vault | HIGH | Phase 2 |  |  |  | 0%
13 | Privilege IAM | Service accounts | NON-COMPLIANT | API uses root for Docker | No dedicated service accounts | Create dedicated service accounts per component | HIGH | Phase 2 |  |  |  | 0%
13 | Privilege IAM | Access review process | NON-COMPLIANT | No periodic reviews | Stale access risk | Implement quarterly access review process | MEDIUM | Phase 2 |  |  |  | 0%
14 | Security Assessment | Vulnerability scanning | NON-COMPLIANT | No automated scanning | Unknown vulnerabilities | Implement Trivy (containers), pip-audit (Python), npm audit (Node) | CRITICAL | Phase 1 |  |  |  | 0%
14 | Security Assessment | Penetration testing | NON-COMPLIANT | No pen test conducted | Untested security posture | Conduct initial pen test before vendor assessment | CRITICAL | Phase 1 |  |  |  | 0%
14 | Security Assessment | npm vulnerabilities | NON-COMPLIANT | 14 known vulns (4 HIGH, 10 MODERATE) | Exploitable frontend dependencies | Run npm audit fix in frontend directory | HIGH | Phase 1 |  |  |  | 0%
14 | Security Assessment | Security scanning in CI/CD | NON-COMPLIANT | No CI/CD pipeline exists | No automated security checks | Add SAST/DAST scanning to CI/CD pipeline | HIGH | Phase 2 |  |  |  | 0%
15 | Application Protection | WAF deployment | NON-COMPLIANT | No WAF configured | No web attack filtering | Deploy AWS WAF with OWASP Core Rule Set | HIGH | Phase 2 |  |  |  | 0%
15 | Application Protection | Bot protection | NON-COMPLIANT | No bot detection | Vulnerable to automated attacks | Implement bot detection/mitigation via WAF | MEDIUM | Phase 2 |  |  |  | 0%
15 | Application Protection | Input filtering | COMPLIANT | Pydantic validation on all endpoints |  |  | N/A | Done |  |  |  | 100%
16 | DDoS/IDS/IPS | DDoS protection | NON-COMPLIANT | No DDoS protection service | Vulnerable to volumetric attacks | Enable AWS Shield Standard (free); consider CloudFront | HIGH | Phase 2 |  |  |  | 0%
16 | DDoS/IDS/IPS | IDS | NON-COMPLIANT | No intrusion detection | Cannot detect attacks | Deploy AWS GuardDuty or Suricata | HIGH | Phase 2 |  |  |  | 0%
16 | DDoS/IDS/IPS | Rate limiting | PARTIAL | Application-level only, in-memory | Not distributed, lost on restart | Migrate rate limiting to Redis for distributed enforcement | HIGH | Phase 1 |  |  |  | 40%
17 | Capacity Management | Infrastructure inventory | PARTIAL | Docker Compose defines services | No formal asset registry | Create comprehensive asset/software inventory | MEDIUM | Phase 3 |  |  |  | 40%
17 | Capacity Management | SBOM | NON-COMPLIANT | No Software Bill of Materials | Cannot track component risks | Generate SBOM using syft or cdxgen | MEDIUM | Phase 3 |  |  |  | 0%
17 | Capacity Management | Resource monitoring | NON-COMPLIANT | No utilization monitoring | Cannot plan capacity | Set up Prometheus + Grafana or CloudWatch monitoring | MEDIUM | Phase 3 |  |  |  | 0%
18 | Communication | Email service | PARTIAL | SendGrid prepared but not active | No email delivery | Activate SendGrid with production API key | MEDIUM | Phase 3 |  |  |  | 30%
18 | Communication | SPF/DKIM/DMARC | NON-COMPLIANT | Not configured | Email spoofing risk | Configure SPF, DKIM, DMARC for a64core.com | MEDIUM | Phase 3 |  |  |  | 0%
19 | Supplier Relationship | SLA definitions | NON-COMPLIANT | No SLAs defined | No service level commitments | Define SLAs (uptime, response time, support levels) | HIGH | Phase 2 |  |  |  | 0%
19 | Supplier Relationship | Rights to audit | NON-COMPLIANT | No audit clause | Cannot verify vendor compliance | Include right-to-audit clause in all agreements | HIGH | Phase 2 |  |  |  | 0%
19 | Supplier Relationship | Maintenance windows | NON-COMPLIANT | No downtime windows defined | Unplanned maintenance risk | Document agreed maintenance/downtime windows | MEDIUM | Phase 2 |  |  |  | 0%
20 | Availability Mgmt | High availability | NON-COMPLIANT | Single instance deployment | Single point of failure | Implement multi-AZ deployment with MongoDB replica set | HIGH | Phase 2 |  |  |  | 0%
20 | Availability Mgmt | Load balancing | NON-COMPLIANT | No load balancer | Cannot distribute traffic | Deploy AWS ALB or Nginx load balancing | HIGH | Phase 2 |  |  |  | 0%
20 | Availability Mgmt | Uptime monitoring | NON-COMPLIANT | No external monitoring | Cannot detect outages | Set up UptimeRobot/Pingdom external monitoring | MEDIUM | Phase 2 |  |  |  | 0%
21 | Segregated Envs | Network segmentation | PARTIAL | Docker bridge network isolates containers | All on same host | Implement VPC with public/private subnets | HIGH | Phase 2 |  |  |  | 30%
21 | Segregated Envs | Database isolation | NON-COMPLIANT | Database ports exposed to host | DB accessible from outside Docker | Remove port mapping for 27017, 3306, 6379 in production | HIGH | Phase 1 |  |  |  | 0%
21 | Segregated Envs | DMZ architecture | NON-COMPLIANT | No DMZ implemented | No security zones | Create DMZ for public-facing services | MEDIUM | Phase 2 |  |  |  | 0%
22 | Policy Compliance | Password policy | COMPLIANT | 8+ chars, complexity enforced in code |  |  | N/A | Done |  |  |  | 100%
22 | Policy Compliance | ISO 27001 compliance | NON-COMPLIANT | No ISO certification or mapping | No formal ISMS | Map controls to ISO 27001 Annex A; consider certification roadmap | HIGH | Phase 3 |  |  |  | 0%
22 | Policy Compliance | UAE PDPL compliance | NON-COMPLIANT | No regulatory compliance docs | Data protection law gaps | Assess UAE Personal Data Protection Law compliance | HIGH | Phase 3 |  |  |  | 0%
22 | Policy Compliance | Security policy document | PARTIAL | Security checklist + risk plan exist | No comprehensive InfoSec policy | Create formal Information Security Policy | MEDIUM | Phase 3 |  |  |  | 30%
23 | RBAC & SoD | RBAC implementation | COMPLIANT | 5-level hierarchy with middleware enforcement |  |  | N/A | Done |  |  |  | 100%
23 | RBAC & SoD | Permission matrix | COMPLIANT | Documented in User-Structure.md |  |  | N/A | Done |  |  |  | 100%
23 | RBAC & SoD | SoD enforcement | PARTIAL | Role hierarchy prevents some conflicts | No formal SoD matrix | Create formal Segregation of Duties matrix | MEDIUM | Phase 2 |  |  |  | 30%
23 | RBAC & SoD | Access review | NON-COMPLIANT | No periodic access review | Stale permissions risk | Schedule quarterly access reviews | MEDIUM | Phase 2 |  |  |  | 0%
24 | Data Security | Data classification | PARTIAL | Data Classification Policy created (Docs/2-Working-Progress/Data-Classification-Policy.md) with 4-tier classification (Restricted/Confidential/Internal/Public), complete PII inventory across 25+ collections, UAE regulatory considerations for Emirates ID. Data Flow Diagrams created (Docs/2-Working-Progress/Data-Flow-Diagrams.md) with system context, auth flows, HR flows, sales flows, cross-module flows, external integration flows, data-at-rest/transit maps, retention policy. Gaps identified: field-level encryption for emiratesId/salary, data masking middleware, retention enforcement. | Cannot apply appropriate controls | Create data classification policy (Public/Internal/Confidential/Restricted) | HIGH | Phase 2 |  |  |  | 50%
24 | Data Security | Data flow analysis | NON-COMPLIANT | No data flow diagrams | Cannot identify exposure points | Create data flow diagrams for all sensitive data | HIGH | Phase 2 |  |  |  | 0%
24 | Data Security | PII management | PARTIAL | Passwords excluded from responses | No PII inventory | Identify and inventory all PII fields | MEDIUM | Phase 2 |  |  |  | 30%
24 | Data Security | DLP controls | NON-COMPLIANT | No DLP | Data exfiltration risk | Implement DLP controls for sensitive data | MEDIUM | Phase 3 |  |  |  | 0%
25 | Security Architecture | Architecture documentation | COMPLIANT | System-Architecture.md (61KB comprehensive) |  |  | N/A | Done |  |  |  | 100%
25 | Security Architecture | Security zones | NON-COMPLIANT | No security zone definitions | No trust boundary documentation | Define security zones: DMZ, application, data tiers | MEDIUM | Phase 3 |  |  |  | 0%
25 | Security Architecture | Threat modeling | NON-COMPLIANT | No formal threat model | Unknown threat landscape | Conduct STRIDE threat modeling exercise | MEDIUM | Phase 3 |  |  |  | 0%
25 | Security Architecture | Cloud security assessment | NON-COMPLIANT | No cloud security review | AWS misconfigurations possible | Conduct AWS Well-Architected Review (Security pillar) | MEDIUM | Phase 3 |  |  |  | 0%

## Remediation Roadmap
# | Phase | Action Item | Control Area(s) | Priority | Effort (Days) | Owner | Status | Target Date | Completion Date | Notes
1 | Phase 1 | Implement automated daily database backups (MongoDB + MySQL) | Data Protection (6) | CRITICAL | 3 |  | In Progress |  |  | Backup scripts + Docker service created 2026-02-04; S3 upload pending
2 | Phase 1 | Create backup encryption and off-site storage | Data Protection (6) | CRITICAL | 2 |  | Not Started |  |  | Blocked on backup S3 integration
3 | Phase 1 | Document and test restore procedures | Data Protection (6) | CRITICAL | 2 |  | In Progress |  |  | Restore script + README created 2026-02-04; first test pending
4 | Phase 1 | Implement TOTP-based MFA for admin roles | Auth & AuthZ (10) | CRITICAL | 5 |  | Not Started |  |  | Google Authenticator/Authy
5 | Phase 1 | Set strong production SECRET_KEY (fail-fast) | Auth & AuthZ (10) | CRITICAL | 1 |  | Completed |  | 2026-02-04 | model_validator added to settings.py 2026-02-04; rejects default key in non-dev
6 | Phase 1 | Create BIA, DR plan, define RTO/RPO | BC & DR (11) | CRITICAL | 5 |  | In Progress |  |  | BIA + DR plan templates created 2026-02-04; pending org review
7 | Phase 1 | Run vulnerability scans (Trivy, pip-audit, npm audit) | Security Assessment (14) | CRITICAL | 2 |  | Completed |  | 2026-02-04 | pip-audit: 17/19 CVEs fixed (2 blocked upstream); npm: 8 moderate dev-only remain
8 | Phase 1 | Fix 14 npm vulnerabilities | Security Assessment (14) | HIGH | 1 |  | Partial |  |  | 8 moderate dev-only vulns remain (vite/esbuild/vue-tsc); require vite 7.x major upgrade
9 | Phase 1 | Add HSTS, CSP, Permissions-Policy headers to Nginx | Security Hardening (8) | HIGH | 1 |  | Completed |  | 2026-02-04 | HSTS+CSP+PermPolicy+XPCDP added to both nginx configs 2026-02-04
10 | Phase 1 | Enable MongoDB authentication | Database Security (9) | CRITICAL | 2 |  | Completed |  | 2026-02-04 | Auth enabled: init-user.js + --auth flag in prod 2026-02-04
11 | Phase 1 | Restrict database ports in production | Segregated Envs (21) | HIGH | 1 |  | Completed |  | 2026-02-04 | MongoDB/Redis ports:[] in prod, Adminer disabled, Registry localhost-only 2026-02-04
12 | Phase 1 | Migrate rate limiting to Redis | DDoS Protection (16) | HIGH | 3 |  | Completed |  | 2026-02-04 | Redis INCR+EXPIRE sliding window + login attempt lists 2026-02-04
13 | Phase 2 | Set up GitHub Actions CI/CD pipeline | SDLC (3) | HIGH | 5 |  | In Progress |  |  | security-scan.yml + build.yml created 2026-02-04; deploy stage pending
14 | Phase 2 | Deploy AWS WAF with OWASP Core Rule Set | WAF (15) | HIGH | 3 |  | Not Started
15 | Phase 2 | Enable AWS Shield Standard + GuardDuty | DDoS/IDS (16) | HIGH | 2 |  | Not Started |  |  | Shield Standard is free
16 | Phase 2 | Set up centralized logging (ELK/CloudWatch) | Log Monitoring (7) | HIGH | 5 |  | Not Started |  |  | Include audit logging
17 | Phase 2 | Integrate with SIEM solution | Log Monitoring (7) | HIGH | 5 |  | Not Started |  |  | AWS SecurityHub or Splunk
18 | Phase 2 | Implement MongoDB replica set | Availability (20) | HIGH | 3 |  | Not Started |  |  | Minimum 3 nodes
19 | Phase 2 | Deploy load balancer (AWS ALB) | Availability (20) | HIGH | 3 |  | Not Started
20 | Phase 2 | Create data flow diagrams | Data Security (24) | HIGH | 3 |  | Not Started
21 | Phase 2 | Create data classification policy | Data Security (24) | HIGH | 2 |  | Not Started
22 | Phase 2 | Define SLAs and audit clauses | Supplier (19) | HIGH | 3 |  | Not Started
23 | Phase 2 | Implement SSO (SAML/OIDC) | Auth & AuthZ (10) | HIGH | 10 |  | Not Started
24 | Phase 2 | Create staging environment | SDLC (3) | HIGH | 3 |  | Not Started |  |  | docker-compose.staging.yml
25 | Phase 2 | Implement VPC with public/private subnets | Segregated Envs (21) | HIGH | 5 |  | Not Started
26 | Phase 2 | Implement password vault (Secrets Manager) | Privilege IAM (13) | HIGH | 3 |  | Not Started
27 | Phase 2 | Conduct initial penetration test | Security Assessment (14) | CRITICAL | 5 |  | Not Started |  |  | External firm recommended
28 | Phase 3 | Enable database encryption at rest | Cryptography (1) | HIGH | 3 |  | Not Started |  |  | WiredTiger + MySQL TDE
29 | Phase 3 | Implement key management (AWS KMS) | Cryptography (1) | HIGH | 5 |  | Not Started
30 | Phase 3 | Set up cert auto-renewal + monitoring | Certificate Mgmt (2) | MEDIUM | 2 |  | Not Started |  |  | Certbot cron + alerts
31 | Phase 3 | Map controls to ISO 27001 Annex A | Policy Compliance (22) | HIGH | 5 |  | Not Started
32 | Phase 3 | Assess UAE PDPL compliance | Policy Compliance (22) | HIGH | 5 |  | Not Started
33 | Phase 3 | Conduct STRIDE threat modeling | Security Architecture (25) | MEDIUM | 3 |  | Not Started
34 | Phase 3 | Generate SBOM and license compliance scan | Capacity Mgmt (17) | MEDIUM | 2 |  | Not Started
35 | Phase 3 | Configure SPF/DKIM/DMARC for email | Communication (18) | MEDIUM | 2 |  | Not Started
36 | Phase 3 | Set up Prometheus + Grafana monitoring | Capacity Mgmt (17) | MEDIUM | 5 |  | Not Started
37 | Phase 3 | AWS Well-Architected Review (Security) | Security Architecture (25) | MEDIUM | 3 |  | Not Started

## Evidence Log
# | Control Area | Sub-Control | Evidence Type | File Path / Reference | Description | Verified By | Date Verified | Notes
1 | Cryptography | Password hashing | Code | src/utils/security.py:17-52 | bcrypt cost factor 12 implementation
2 | Cryptography | License encryption | Code | src/utils/encryption.py | Fernet AES-128-CBC with PBKDF2
3 | Certificate Mgmt | SSL/TLS config | Config | nginx/nginx.prod.conf | TLSv1.2/1.3, ECDHE ciphers
4 | Certificate Mgmt | Let's Encrypt certs | Config | /etc/letsencrypt/live/a64core.com/ | Production SSL certificates
5 | SDLC | Source control | Config | .gitignore | Git repo with proper exclusions
6 | SDLC | Environment separation | Config | docker-compose.yml, docker-compose.prod.yml | Dev and prod Docker configs
7 | Security Hardening | Input validation | Code | src/models/user.py | Pydantic models on all endpoints
8 | Security Hardening | Security headers | Config | nginx/nginx.dev.conf:13-17 | X-Content-Type, X-Frame, XSS-Protection, Referrer
9 | Security Hardening | Non-root container | Config | Dockerfile:36-39 | appuser UID 1000
10 | Auth & AuthZ | JWT implementation | Code | src/utils/security.py:55-99 | HS256 access tokens, 1h expiry
11 | Auth & AuthZ | Password policy | Code | src/models/user.py:51-66 | 8+ chars, complexity validation
12 | Auth & AuthZ | Account lockout | Code | src/middleware/rate_limit.py:146-220 | 5 attempts, 15-min lockout
13 | Auth & AuthZ | RBAC | Code | src/middleware/permissions.py | 5-level role hierarchy
14 | Auth & AuthZ | Refresh token rotation | Code | src/services/auth_service.py:256-382 | One-time use rotating tokens
15 | Auth & AuthZ | Email enumeration prevention | Code | src/api/v1/auth.py:249-272 | Password reset always returns success
16 | Database Security | Query safety | Code | Motor/PyMongo driver usage | No raw SQL; Pydantic input validation
17 | Remote Access | SSH key auth | Config | a64-platform-key.pem | PEM-based SSH authentication
18 | Remote Access | IP restriction | Script | update-ssh-access.sh | AWS Security Group IP update
19 | Log Monitoring | Container logging | Config | docker-compose.yml (logging section) | JSON-file driver, 10MB rotation
20 | Security Arch | Architecture docs | Document | Docs/1-Main-Documentation/System-Architecture.md | 61KB comprehensive architecture doc
21 | RBAC & SoD | Permission matrix | Document | Docs/1-Main-Documentation/User-Structure.md | Endpoint permission mapping
22 | Hosting | Cloud hosting | Infrastructure | AWS me-central-1 | UAE region deployment
23 | Data Protection | Soft delete | Code | src/services/user_service.py | 90-day user recovery
24 | Application Protection | Input validation | Code | All API endpoint models | Pydantic validation on 43+ endpoints
25 | Security Hardening | HSTS + CSP + Permissions-Policy | Config | nginx/nginx.prod.conf:14-21, nginx/nginx.dev.conf:14-20 | Added HSTS (1yr+preload), CSP, Permissions-Policy, X-Permitted-Cross-Domain-Policies headers | Claude Code | 2026-02-04
26 | Security Hardening | SECRET_KEY production validator | Code | src/config/settings.py:54-63 | model_validator rejects default SECRET_KEY and DEBUG=True in non-development environments | Claude Code | 2026-02-04
27 | Security Hardening | Upload size limit reduced | Config | nginx/nginx.prod.conf:88 | client_max_body_size reduced from 100M to 20M in production | Claude Code | 2026-02-04
28 | Database Security | MongoDB authentication | Config | mongo-init/init-user.js, docker-compose.prod.yml | Dedicated a64core_app user (readWrite), root auth, --auth flag in production | Claude Code | 2026-02-04
29 | Security Hardening | Database port closure | Config | docker-compose.prod.yml | MongoDB/Redis ports:[], Adminer profiles:donotstart, Registry 127.0.0.1 only | Claude Code | 2026-02-04
30 | Auth & AuthZ | Redis-backed rate limiting | Code | src/middleware/rate_limit.py | Redis INCR+EXPIRE sliding window, login attempt lists with 15-min TTL, in-memory fallback | Claude Code | 2026-02-04
31 | Data Protection | Backup infrastructure | Script | scripts/backup/mongodb_backup.sh, mongodb_restore.sh, docker/backup/Dockerfile | Automated daily 2AM UTC backups, 7/4/3 retention, gzip compression | Claude Code | 2026-02-04
32 | SDLC | CI/CD security scanning | Config | .github/workflows/security-scan.yml, build.yml | GitHub Actions: black, flake8, pip-audit, npm audit, Trivy, Docker build | Claude Code | 2026-02-04
33 | BC & DR | BIA template | Document | Docs/2-Working-Progress/Business-Impact-Analysis.md | Process-to-component mapping, impact assessment, recovery priorities | Claude Code | 2026-02-04
34 | BC & DR | DR plan with runbooks | Document | Docs/2-Working-Progress/Disaster-Recovery-Plan.md | RTO:4h/RPO:1h, 4 disaster runbooks, quarterly DR test schedule | Claude Code | 2026-02-04
35 | Security Hardening | Hardcoded credentials removed | Config | docker-compose.yml (cron service) | ADMIN_PASSWORD changed from hardcoded to ${ADMIN_PASSWORD} env var reference | Claude Code | 2026-02-04
36 | Security Assessment | Python dependency audit (pip-audit) | Scan Report | requirements.txt (all 14 packages updated) | pip-audit: 17/19 CVEs resolved. Remaining: protobuf (blocked by aiplatform <6.0 pin), ecdsa (upstream wontfix). Updated: fastapi 0.128.0, cryptography 44.0.1, requests 2.32.5, pymongo 4.9.2, python-jose 3.5.0, python-multipart 0.0.22, + 8 others | Claude Code | 2026-02-04
37 | Security Assessment | npm dependency audit | Scan Report | frontend/user-portal/package.json | npm audit: 8 moderate dev-only vulnerabilities (esbuild/vite/vue-tsc). All are build tools not shipped to production. Fix requires vite 5→7 major upgrade. | Claude Code | 2026-02-04
38 | Security Assessment | Dependency version updates | Code | requirements.txt (14 packages bumped) | fastapi 0.109→0.128, cryptography 41.0.7→44.0.1, requests 2.31→2.32.5, pymongo 4.6.1→4.9.2, motor 3.3.2→3.6.0, aiomysql 0.2→0.3.2, python-jose 3.3→3.5, python-multipart 0.0.6→0.0.22, black 24.1→25.1, redis 5.0.1→5.2.1, pydantic 2.5.3→2.10.4, uvicorn 0.27→0.34, httpx 0.26→0.28.1, google-cloud-aiplatform 1.40→1.75 | Claude Code | 2026-02-04
39 | Data Security | Data classification | Documentation | Docs/2-Working-Progress/Data-Classification-Policy.md, Docs/2-Working-Progress/Data-Flow-Diagrams.md | Created Data Classification Policy with complete PII inventory (4 tiers, 25+ collections mapped) and Data Flow Diagrams (7 flow diagrams, transit/rest analysis, security gap identification) | System | 2026-02-04 | Policy and diagrams complete. Pending: field-level encryption, data masking, retention automation